## Slide 1
Baloise CI/CD Project
13th October 2020
Status

## Slide 2: Objective
To create an environment in Cloud Native Lab for provisioning of infrastructure and applications for Baloise. The assumption is this will allow Baloise to try out CI/CD ahead of the completion of new data centres readiness. It is expected the environment will be needed until March/April 2021.
We will start with an MVP that can then be extended over the next few months to include more tooling and to showcase further automation. Initially we will be provisioning vSphere VMs running in the Labs private cloud.

## Slide 3: In-Scope and Out of Scope
In scope MVP
In the Cloud
  A source code repository. Our current expectation is Bitbucket will not be used. We will use a Baloise private GIThub account. Baloise will provide access to the repo and the code that they are prepared to share in our Labs environment. The Cloud Native Labs are supported by / accessed by non European (US and India based) resources.
  Jira/concourse- Baloise owned – for running Kanban and storing documentation. Users named below will need access.
To be built by Developers- Local IDE on Laptops for code edit/ commit to GitHub. (no assumption made on IDE)
To be deployed in the London Lab
Jenkins- Admin account needed for installing plugins
MyCloud
Ansible / AWX (Ansible Tower)- VM will be provided
The following MVP integration tooling will also be deployed:
Nexus OSS—Needed for artifacts
Out of scope for MVP
Service Now instance / integration
Prometheus (monitoring)
ELK logging and dashboard
Splunk Logging
Open shift and any CI/CD related to containerisation / container repos / container deployment
Provisioning VMs on public cloud or a second Labs site.

## Slide 4: VM Requirement
Pilot Application Name: Corelia
  Number of VM’s needed: 2
  OS : RHEL ( Version >= 7 )
  Configuration (vCPU, memory (GB) of each VM: T-Shirt size small ( ~ 1 vCPU/4GB RAM )
  Jboss on webserver VM and Postgre database on DB VM
VM’s needed for supporting components:
  2x MS-Windows Server for MyCloud
  1x Linux RedHat-based Server- AWX
  1x Linux RedHat-based Server for Nexus OSS
  1x Linux RedHat-based Server for Jenkins

## Slide 5: Deliveries Achieved
VPN Accesses
10 members of HCL
1 member of CNL
8 members of Baloise
Virtual Machines
2x MS-Windows Server
  IIS (for MyCloud)
  SQL Server (for MyCloud)
1x Linux RedHat-based Server
  AWX
2x Linux RedHat-based Server
  Nexus OSS
  Jenkins

## Slide 6: Deliveries In Progress
Pre-reqs for MyCloud- (Expected delivery date: 15th October 2020)

## Slide 7: Hardware Overview in Lab
Hardware
14 CPU
32GB RAM
620GB SAN Storage
System
VPN Juniper System
Dell VxRail Cluster

## Slide 8: Timeline for Setup
Readiness Steps | Week41 | Week42 | Week43 | Week44 | Week45
VM Requirement finalization |  |  |  |  | 
VM Readiness for mycloud, jenkins, ansible, Nexus |  |  |  |  | 
Installation- mycloud, jenkins, ansible, Nexus |  |  |  |  | 
Environment Readiness with Integration |  |  |  |  | 
Integrated Testing |  |  |  |  | 

## Slide 9: Open Points/Clarifications Needed
For Ansible- Jboss and Postgres (2 use cases)- Basic installation required or any customization is required
  N or N-1 version or rpms for jboss will be provided by Baloise
  Jboss version 7.3 will be used as per HLD
Is there any application requirement for LDAP or AD?
Access for Baloise users through VPN- Baloise to confirm if they are able to access.
  Jan will check access through VPN